# Samples

## Sample Project Decisions

Moved all Automation epic tasks to not-selected status.

Sprint 13

Date - 9/12/2023

Decision made by:

EM

Decision: Removed 16.5 story points worth of stories from the sprint. Reason: overcommitment during planning.

CC: ,

Developer

SM

Date - 9/14/2023

Decision made by:

Decision: DevOps and deployment architecture implementation and Reports functionalities has to be a part of phase 1. CC:

COO

Sprint 14

**Date - 9/26/2023**

Decision made by:

EM

Decision:

→ Before starting a sprint, frontend developer, backend developer and tester should be assigned to each story.

→ Decided to clear out all the spilled over stories and setup sprint goals for that.

Date - 10/05/2023

Decision made by:

EM

Decision:

→ There should be a way to review the completed work against the sprint goals during the middle of the sprint. (Preferably send an email to the EM)

## Sprint plan sample (From Transpomate)

##### Sprint goals:

 Complete spilled over mobile + web stories (SC - 4 / SP - 13)- Developer , Developer ,

 Achieve 46 SPs - (13 SP (4) spillovers + 36SP (8) new items)

 Complete R&D task on SMS service comparison and provide a summary of the findings - points - 3)

(Story

Developer2

##### Sprint summary:

|  |  |
| --- | --- |
| total spillover stories points / count | 13 SP / 4 - Developer , Developer2 |
| total new stories points/count | 33 SP / 8 - Developer , Developer2 |
| current velocity | 20.2 SP |
| commitment | 46 SP (commitment is 33 + spillovers) |
| dependency status | TN-602  Acceptance criteria needs to be updated. BA **PENDING**  UI design - BA **PENDING**  Error page should be designed to show if the login feature is crashed.  Not access page should be designed to show if the user has the access to login or not.  Sequence diagram - Developer TN-592  R&D on how to create a secure URL to  upload files - Developer **PENDING**  R&D on how to clear the files stored in the server side. Developer **PENDING**  More information → [Issue Dependencies - Sprint 15](https://inivos.atlassian.net/wiki/spaces/T/pages/109051905) |

**Spill overs:**

**Key Summary T Created Updated Due Assignee Reporter P Status Resolution**

[No issues found](https://inivos.atlassian.net/issues/?jql=Project%2B%3D%2B%22Transpomate%2BNew%22%2Band%2Btype%2Bin%2B%28Bug%2C%2BStory%2C%2BTask%29%2Band%2Bstatus%2Bnot%2Bin%2B%28Done%29%2Band%2Bsprint%2B%3D%2B152%2B%2B%2B%2B%2B%2B%2B%2B&src=confmacro)

##### New tasks:

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Key** | **Summary** | **Assignee** | **Reporter** | **Frontend Dev.** | **Backend Dev.** | **Tester** | **Story Points** | **Status T Due Lab** |
| [TN-804](https://inivos.atlassian.net/browse/TN-804) | [[UI[Status] - Toggle](https://inivos.atlassian.net/browse/TN-804) | QA | QA | Sasani |  | QA |  | **DONE** |
|  | [alignment should be](https://inivos.atlassian.net/browse/TN-804) |  |  | Jayathilake |  |  |  |  |
|  | [center.](https://inivos.atlassian.net/browse/TN-804) |  |  |  |  |  |  |  |
| [TN-793](https://inivos.atlassian.net/browse/TN-793) | [[Trip History] - The](https://inivos.atlassian.net/browse/TN-793) | QA | QA |  |  |  |  | **DONE** |
|  | [added trip request is](https://inivos.atlassian.net/browse/TN-793) |  |  |  |  |  |  |  |
|  | [not visible on the trip](https://inivos.atlassian.net/browse/TN-793) |  |  |  |  |  |  |  |
|  | [history page.](https://inivos.atlassian.net/browse/TN-793) |  |  |  |  |  |  |  |
| [TN-792](https://inivos.atlassian.net/browse/TN-792) | [[User][Status] - The](https://inivos.atlassian.net/browse/TN-792) | QA | QA |  |  |  |  | **DONE** |
|  | [user can login to the](https://inivos.atlassian.net/browse/TN-792) |  |  |  |  |  |  |  |
|  | [system successfully](https://inivos.atlassian.net/browse/TN-792) |  |  |  |  |  |  |  |
|  | [after being disabled.](https://inivos.atlassian.net/browse/TN-792) |  |  |  |  |  |  |  |
| [TN-791](https://inivos.atlassian.net/browse/TN-791) | [R&D on SMS services](https://inivos.atlassian.net/browse/TN-791) | Thambara Supun | BA | Thambara Supun |  |  |  | **DONE** |
|  |  | Basnayake |  | Basnayake |  |  |  |  |
| [TN-787](https://inivos.atlassian.net/browse/TN-787) | [[UI] - The ID column](https://inivos.atlassian.net/browse/TN-787) | QA2 | QA |  |  |  |  | **DONE** |
|  | [should be removed.](https://inivos.atlassian.net/browse/TN-787) |  |  |  |  |  |  |  |
| [TN-782](https://inivos.atlassian.net/browse/TN-782) | [[Add Vehicle] -](https://inivos.atlassian.net/browse/TN-782) | QA | QA | Sasani |  | QA |  | **DONE** |
|  | [Validation messages](https://inivos.atlassian.net/browse/TN-782) |  |  | Jayathilake |  |  |  |  |
|  | [should display in](https://inivos.atlassian.net/browse/TN-782) |  |  |  |  |  |  |  |
|  | [particular fields when](https://inivos.atlassian.net/browse/TN-782) |  |  |  |  |  |  |  |
|  | [saving with invalid](https://inivos.atlassian.net/browse/TN-782) |  |  |  |  |  |  |  |
|  | [data.](https://inivos.atlassian.net/browse/TN-782) |  |  |  |  |  |  |  |
| [TN-781](https://inivos.atlassian.net/browse/TN-781) | [[Edit Vehicle] - Vehicles](https://inivos.atlassian.net/browse/TN-781) | QA | QA | Sasani |  | QA |  | **DONE** |
|  | [should not be saved](https://inivos.atlassian.net/browse/TN-781) |  |  | Jayathilake |  |  |  |  |
|  | [with zeros in the "no](https://inivos.atlassian.net/browse/TN-781) |  |  |  |  |  |  |  |
|  | [seat" and "cost per km"](https://inivos.atlassian.net/browse/TN-781) |  |  |  |  |  |  |  |
|  | [fields.](https://inivos.atlassian.net/browse/TN-781) |  |  |  |  |  |  |  |
| [TN-780](https://inivos.atlassian.net/browse/TN-780) | [[UI][All Modules] -](https://inivos.atlassian.net/browse/TN-780) | QA | QA | Sasani |  | QA |  | **DONE** |
|  | [Validation messages](https://inivos.atlassian.net/browse/TN-780) |  |  | Jayathilake |  |  |  |  |
|  | [are not in the correct](https://inivos.atlassian.net/browse/TN-780) |  |  |  |  |  |  |  |
|  | [capitalization.](https://inivos.atlassian.net/browse/TN-780) |  |  |  |  |  |  |  |
| [TN-777](https://inivos.atlassian.net/browse/TN-777) | [[UI][Admin][All](https://inivos.atlassian.net/browse/TN-777) | QA2 | QA2 | Sasani |  | QA2 |  | **DONE** |
|  | [Modules]-The gap](https://inivos.atlassian.net/browse/TN-777) |  |  | Jayathilake |  |  |  |  |
|  | [between all the fields](https://inivos.atlassian.net/browse/TN-777) |  |  |  |  |  |  |  |
|  | [of add employees are](https://inivos.atlassian.net/browse/TN-777) |  |  |  |  |  |  |  |
|  | [not same as figma](https://inivos.atlassian.net/browse/TN-777) |  |  |  |  |  |  |  |
| [TN-773](https://inivos.atlassian.net/browse/TN-773) | [[Suggestion][UI][All](https://inivos.atlassian.net/browse/TN-773) | QA | QA |  |  |  |  | **DONE** |
|  | [Modules] - Lack of](https://inivos.atlassian.net/browse/TN-773) |  |  |  |  |  |  |  |
|  | [separation between](https://inivos.atlassian.net/browse/TN-773) |  |  |  |  |  |  |  |
|  | [title and fields.](https://inivos.atlassian.net/browse/TN-773) |  |  |  |  |  |  |  |
| [TN-692](https://inivos.atlassian.net/browse/TN-692) | [[UI][Vehicle] - The](https://inivos.atlassian.net/browse/TN-692) | QA2 | QA |  |  |  |  | **DONE** |
|  | [name of the 7th](https://inivos.atlassian.net/browse/TN-692) |  |  |  |  |  |  |  |
|  | [column is not as figma.](https://inivos.atlassian.net/browse/TN-692) |  |  |  |  |  |  |  |
| [TN-674](https://inivos.atlassian.net/browse/TN-674) | [[All Modules]- The](https://inivos.atlassian.net/browse/TN-674) | QA | QA |  |  |  |  | **DONE** |
|  | [latest data should be](https://inivos.atlassian.net/browse/TN-674) |  |  |  |  |  |  |  |
|  | [visible at the top of the](https://inivos.atlassian.net/browse/TN-674) |  |  |  |  |  |  |  |
|  | [list.](https://inivos.atlassian.net/browse/TN-674) |  |  |  |  |  |  |  |

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| [TN-673](https://inivos.atlassian.net/browse/TN-673) | [As an Admin, I need to](https://inivos.atlassian.net/browse/TN-673) | QA | BA | dileepa.mabulage | dileepa.mabulage | QA | 8.0 | **DONE** |  | |
|  | [access only the](https://inivos.atlassian.net/browse/TN-673) |  |  |  |  |  |  |  |
|  | [functions assigned to](https://inivos.atlassian.net/browse/TN-673) |  |  |  |  |  |  |  |
|  | [me, So that I can do](https://inivos.atlassian.net/browse/TN-673) |  |  |  |  |  |  |  |
|  | [the specific assigned](https://inivos.atlassian.net/browse/TN-673) |  |  |  |  |  |  |  |
|  | [functions within the](https://inivos.atlassian.net/browse/TN-673) |  |  |  |  |  |  |  |
|  | [system.](https://inivos.atlassian.net/browse/TN-673) |  |  |  |  |  |  |  |
| [TN-671](https://inivos.atlassian.net/browse/TN-671) | [[UI][Edit Owner] - The](https://inivos.atlassian.net/browse/TN-671) | QA | QA |  |  |  |  | **DONE** |  |  |
|  | [error message is not in](https://inivos.atlassian.net/browse/TN-671) |  |  |  |  |  |  |  |  |  |
|  | [correct capitalization.](https://inivos.atlassian.net/browse/TN-671) |  |  |  |  |  |  |  |  |  |
| [TN-669](https://inivos.atlassian.net/browse/TN-669) | [[UI][View Vehicle]- The](https://inivos.atlassian.net/browse/TN-669) | QA | QA |  |  |  |  | **DONE** |  |  |
|  | [column names are not](https://inivos.atlassian.net/browse/TN-669) |  |  |  |  |  |  |  |  |  |
|  | [in the correct](https://inivos.atlassian.net/browse/TN-669) |  |  |  |  |  |  |  |  |  |
|  | [capitalization.](https://inivos.atlassian.net/browse/TN-669) |  |  |  |  |  |  |  |  |  |
| [TN-666](https://inivos.atlassian.net/browse/TN-666) | [[Email] - The email](https://inivos.atlassian.net/browse/TN-666) | QA | QA |  |  |  |  | **DONE** |  |  |
|  | [does not contain the](https://inivos.atlassian.net/browse/TN-666) |  |  |  |  |  |  |  |  |  |
|  | [accurate timezone](https://inivos.atlassian.net/browse/TN-666) |  |  |  |  |  |  |  |  |  |
| [TN-627](https://inivos.atlassian.net/browse/TN-627) | [As a Manager, I need](https://inivos.atlassian.net/browse/TN-627) | QA | BA | Thambara Supun | Thambara Supun | QA | 3.0 | **DONE** |  |  |
|  | [to receive an email, So](https://inivos.atlassian.net/browse/TN-627) |  |  | Basnayake | Basnayake |  |  |  |  |  |
|  | [that I am notified that](https://inivos.atlassian.net/browse/TN-627) |  |  |  |  |  |  |  |  |  |
|  | [an employee has](https://inivos.atlassian.net/browse/TN-627) |  |  |  |  |  |  |  |  |  |
|  | [requested a trip.](https://inivos.atlassian.net/browse/TN-627) |  |  |  |  |  |  |  |  |  |
| [TN-612](https://inivos.atlassian.net/browse/TN-612) | [[CR] As a Transport](https://inivos.atlassian.net/browse/TN-612) | QA | BA | Sasani |  | QA | 1.0 | **DONE** |  |  |
|  | [Coordinator, I need to](https://inivos.atlassian.net/browse/TN-612) |  |  | Jayathilake |  |  |  |  |  |  |
|  | [view all scheduled](https://inivos.atlassian.net/browse/TN-612) |  |  |  |  |  |  |  |  |  |
|  | [voyages, So that I can](https://inivos.atlassian.net/browse/TN-612) |  |  |  |  |  |  |  |  |  |
|  | [manage and](https://inivos.atlassian.net/browse/TN-612) |  |  |  |  |  |  |  |  |  |
|  | [coordinate scheduled](https://inivos.atlassian.net/browse/TN-612) |  |  |  |  |  |  |  |  |  |
|  | [voyages effectively](https://inivos.atlassian.net/browse/TN-612) |  |  |  |  |  |  |  |  |  |
| [TN-602](https://inivos.atlassian.net/browse/TN-602) | [As a Driver, I need to](https://inivos.atlassian.net/browse/TN-602) | Rishimithun | Thanusan | Rishimithun | dileepa.mabulage | QA2 | 8.0 | **DEVELOPMENT IN PROGRESS** | 30/Nov/23 |  |
|  | [validate my email using](https://inivos.atlassian.net/browse/TN-602) | Muralidharan | irran | Muralidharan |  |  |  |  |  |  |
|  | [both Azure](https://inivos.atlassian.net/browse/TN-602) |  |  |  |  |  |  |  |  |  |
|  | [authenticator (MS](https://inivos.atlassian.net/browse/TN-602) |  |  |  |  |  |  |  |  |  |
|  | [authentication app)](https://inivos.atlassian.net/browse/TN-602) |  |  |  |  |  |  |  |  |  |
|  | [and system validator,](https://inivos.atlassian.net/browse/TN-602) |  |  |  |  |  |  |  |  |  |
|  | [So that I can log into](https://inivos.atlassian.net/browse/TN-602) |  |  |  |  |  |  |  |  |  |
|  | [the Mobile app](https://inivos.atlassian.net/browse/TN-602) |  |  |  |  |  |  |  |  |  |
| [TN-592](https://inivos.atlassian.net/browse/TN-592) | [As a mobile tester, I](https://inivos.atlassian.net/browse/TN-592) | QA2 | BA |  | dileepa.mabulage | QA2 | 5.0 | **DONE** |  |  |
|  | [need a backend](https://inivos.atlassian.net/browse/TN-592) |  |  |  |  |  |  |  |  |  |
|  | [endpoint to return a](https://inivos.atlassian.net/browse/TN-592) |  |  |  |  |  |  |  |  |  |
|  | [unique URL to upload](https://inivos.atlassian.net/browse/TN-592) |  |  |  |  |  |  |  |  |  |
|  | [files, So that the files](https://inivos.atlassian.net/browse/TN-592) |  |  |  |  |  |  |  |  |  |
|  | [can be uploaded](https://inivos.atlassian.net/browse/TN-592) |  |  |  |  |  |  |  |  |  |
|  | [securely.](https://inivos.atlassian.net/browse/TN-592) |  |  |  |  |  |  |  |  |  |
| [TN-574](https://inivos.atlassian.net/browse/TN-574) | [[LocalApk][Mobile]](https://inivos.atlassian.net/browse/TN-574) | QA2 | QA2 |  |  |  |  | **DONE** |  | LocalA |
|  | [[Passenger List]-Check](https://inivos.atlassian.net/browse/TN-574) |  |  |  |  |  |  |  |  |  |
|  | [box functions](https://inivos.atlassian.net/browse/TN-574) |  |  |  |  |  |  |  |  |  |
|  | [independent of the](https://inivos.atlassian.net/browse/TN-574) |  |  |  |  |  |  |  |  |  |
|  | [passenger cards](https://inivos.atlassian.net/browse/TN-574) |  |  |  |  |  |  |  |  |  |
| [TN-427](https://inivos.atlassian.net/browse/TN-427) | [As an admin, I want to](https://inivos.atlassian.net/browse/TN-427) | QA | Thanusan | Sasani | Thambara Supun | QA | 3.0 | **DONE** |  |  |
|  | [view the users](https://inivos.atlassian.net/browse/TN-427) |  | irran | Jayathilake | Basnayake |  |  |  |  |  |
|  | [registered to the](https://inivos.atlassian.net/browse/TN-427) |  |  |  |  |  |  |  |  |  |

[system, So that I can](https://inivos.atlassian.net/browse/TN-427) [view user details.](https://inivos.atlassian.net/browse/TN-427)



**DONE**

[TN-225](https://inivos.atlassian.net/browse/TN-225) [As an admin, I want to](https://inivos.atlassian.net/browse/TN-225) [enable and disable](https://inivos.atlassian.net/browse/TN-225) [user, So that they are](https://inivos.atlassian.net/browse/TN-225) [inactive in the system](https://inivos.atlassian.net/browse/TN-225) [once disabled and](https://inivos.atlassian.net/browse/TN-225) [active once enabled](https://inivos.atlassian.net/browse/TN-225)

QA Thanusan

irran

Abdul Qadir QA

2.0

[23 issues](https://inivos.atlassian.net/issues/?jql=Project%2B%3D%2B%22Transpomate%2BNew%22%2Band%2Btype%2Bin%2B%28%27bug%27%2C%2B%27story%27%2C%2B%27task%27%29%2Band%2Bsprint%2B%3D%2B154%2Band%2Bsprint%2Bnot%2Bin%2B%28152%29%2B&src=confmacro)

## Sample Issue Dependency Summary Document (From Transpomate)

|  |  |
| --- | --- |
| Overall status | **URGENT** |
| Total Impacted story count/points. | ~~9 / 44.5~~ |
| Blocked story count / points | ~~1 / 18~~ |
| Current velocity in story points | 16.5 |
| Dependency clearance due date | Sep 22, 2023 **CLEARED** |
| Dependency Score | to-be-decided |

**Issues Impacted**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Key** | **Summary** | **Assignee** | **Reporter** | **Status** | **Frontend** **Dev.** | **Backend Dev.** | **Tester** | **Story Points** |
| [TN-598](https://inivos.atlassian.net/browse/TN-598) | [As an admin, I need to search for users, So that I can](https://inivos.atlassian.net/browse/TN-598) | QA | BA | **DONE** | Sasani Jayathilake | dileepa.mabulage | QA | 5.0 |
|  | [assign the searched user with a role (assigning the](https://inivos.atlassian.net/browse/TN-598) |  |  |  |  |  |  |  |
|  | [role isn't included)](https://inivos.atlassian.net/browse/TN-598) |  |  |  |  |  |  |  |
| [TN-591](https://inivos.atlassian.net/browse/TN-591) | [As a Transport Coordinator, I need to receive an](https://inivos.atlassian.net/browse/TN-591) | QA | BA | **DONE** | Thambara Supun | Thambara Supun | QA | 13.0 |
|  | [automated email, So that I know that the voyage has](https://inivos.atlassian.net/browse/TN-591) |  |  |  | Basnayake | Basnayake |  |  |
|  | [started](https://inivos.atlassian.net/browse/TN-591) |  |  |  |  |  |  |  |
| [TN-561](https://inivos.atlassian.net/browse/TN-561) | [As a Transport Coordinator, I need to create new](https://inivos.atlassian.net/browse/TN-561) | QA | BA | **DONE** | Abdul Qadir | Thambara Supun | QA | 5.0 |
|  | [starting and ending points for a voyage, So that I can](https://inivos.atlassian.net/browse/TN-561) |  |  |  |  | Basnayake |  |  |
|  | [change the voyage route.](https://inivos.atlassian.net/browse/TN-561) |  |  |  |  |  |  |  |
| [TN-513](https://inivos.atlassian.net/browse/TN-513) | [As a Driver, I need to upload the selected image, So](https://inivos.atlassian.net/browse/TN-513) | QA2 | Lithira.Senath | **DONE** | Rishimithun | Rishimithun | QA2 | 5.0 |
|  | [that the TC could use the image to compare with the](https://inivos.atlassian.net/browse/TN-513) |  |  |  | Muralidharan | Muralidharan |  |  |
|  | [odometer text the driver entered.](https://inivos.atlassian.net/browse/TN-513) |  |  |  |  |  |  |  |
| [TN-461](https://inivos.atlassian.net/browse/TN-461) | [As a Driver, I need to verify the attendance of the](https://inivos.atlassian.net/browse/TN-461) | QA2 | Lithira.Senath | **DONE** | Rishimithun | Thambara Supun | QA2 | 3.0 |
|  | [passengers and mark the checkbox if present, So that](https://inivos.atlassian.net/browse/TN-461) |  |  |  | Muralidharan | Basnayake |  |  |
|  | [I can see the pins on the map for the present](https://inivos.atlassian.net/browse/TN-461) |  |  |  |  |  |  |  |
|  | [passengers](https://inivos.atlassian.net/browse/TN-461) |  |  |  |  |  |  |  |
| [TN-346](https://inivos.atlassian.net/browse/TN-346) | [As a Driver, I want to enter the odometer reading, so](https://inivos.atlassian.net/browse/TN-346) | QA2 | Lithira.Senath | **DONE** | Rishimithun | dileepa.mabulage | QA2 | 0.5 |
|  | [that I can start the voyage.](https://inivos.atlassian.net/browse/TN-346) |  |  |  | Muralidharan |  |  |  |
| [TN-345](https://inivos.atlassian.net/browse/TN-345) | [As a Driver, I want to take a picture of the odometer, so](https://inivos.atlassian.net/browse/TN-345) | QA2 | Lithira.Senath | **DONE** | Rishimithun |  | QA2 | 5.0 |
|  | [that I can keep track of the odometer beginning](https://inivos.atlassian.net/browse/TN-345) |  |  |  | Muralidharan |  |  |  |
|  | [reading before starting the voyage.](https://inivos.atlassian.net/browse/TN-345) |  |  |  |  |  |  |  |
| [TN-209](https://inivos.atlassian.net/browse/TN-209) | [As a Driver, I want to drop trips for employees, So that](https://inivos.atlassian.net/browse/TN-209) | QA2 | Thanusan | **DONE** | Rishimithun | Rishimithun | QA2 | 5.0 |
|  | [the mobile app will be notified with each drop and help](https://inivos.atlassian.net/browse/TN-209) |  | irran |  | Muralidharan | Muralidharan |  |  |
|  | [in preparing the report.](https://inivos.atlassian.net/browse/TN-209) |  |  |  |  |  |  |  |
| [TN-207](https://inivos.atlassian.net/browse/TN-207) | [As a Driver, I want to view a list of the passengers, So](https://inivos.atlassian.net/browse/TN-207) | QA2 | Thanusan | **DONE** | Rishimithun | Thambara Supun | QA2 | 3.0 |
|  | [that I know which passengers have been allocated to](https://inivos.atlassian.net/browse/TN-207) |  | irran |  | Muralidharan | Basnayake |  |  |
|  | [the voyage and mark their attendance.](https://inivos.atlassian.net/browse/TN-207) |  |  |  |  |  |  |  |

[9 issues](https://inivos.atlassian.net/issues/?jql=key%2Bin%2B%28%27TN-598%27%2C%2B%27TN-346%27%2C%2B%27TN-513%27%2C%2B%27TN-345%27%2C%2B%27TN-209%27%2C%2B%27TN-461%27%2C%27TN-207%27%2C%27TN-561%27%2C%27TN-591%27%29%2B%2B%2B%2B%2B&src=confmacro)

**Dependencies**

|  |  |  |
| --- | --- | --- |
| **Issue Key** | **Dependancy** | **Status** |
| TN-598 | Sequence Diagram – Developer | **NON-CRITICAL** |
| TN-346 | API keys to be shared with Rishi - Developer - **DONE** Architecture diagram - Architect1  - **DONE** | **DONE** |
| TN-513 | User story / Acceptance Criteria / BA Diagram - BA - **DONE**  Blob storage for the QA environment. Setup QA environment - Developer - **DONE**  Architecture Diagram - Architect1 - **DONE**  Device for QA testing - SM - **DONE**  Sequence Diagram - Developer2 **DONE**  Deployment Diagram - Developer / Architect1 to confirm which deployment method to use. (candidate choices: GitHub actions, azure Devops) | **DONE** |
| TN-345 | QA environment resource provisioning - Developer - **DONE** | **DONE** |
| TN-209 | Architecture Diagram - Architect1 - **DONE**  Sequence Diagram - Developer | **NON-CRITICAL** |
| TN-461 | Database Diagram & Changes - Developer2 -  **DONE**  Sequence Diagram - Developer2 | **NON-CRITICAL** |
| TN-207 | Sequence Diagram - Developer | **NON-CRITICAL** |
| TN-561 | Sequence Diagram - Frontend Developer | **DONE** |
| TN-591 | Create required cloud resources in Dev environment. Pending due to naming convention issue. - Architect1 - **DONE**  Create required cloud resources in QA environment. Pending due to naming | **NON-CRITICAL** |

|  |  |  |
| --- | --- | --- |
|  | convention issue. - Architect1 - **DONE**  Sequence Diagram - Developer2 **DONE**  Deployment Diagram - Developer - **REMOVED**  Happy path test cases - QA2 |  |

## Sample Sprint Review (14/09/2023) meeting notes & action items

Change the distance to units KMs.



**(New story - CR linked to**

[ned), So that I can see and manage all voyages effectively.](https://inivos.atlassian.net/browse/TN-119)

[**DONE**](https://inivos.atlassian.net/browse/TN-119) **119)** / Manage Voyages page **[**

**]**

[TN-612: [CR] As a Transport Coordinator, I need to view all scheduled voyages, So that I can man](https://inivos.atlassian.net/browse/TN-612)

[TN-119: As a Transport Coordinator, I want to view all voyages (scheduled, completed, ongoing, and abando](https://inivos.atlassian.net/browse/TN-119)

[age and coordinate scheduled voyages effectively](https://inivos.atlassian.net/browse/TN-612) [**DONE**](https://inivos.atlassian.net/browse/TN-612)

Add starting odometer reading instead of ending odometer reading. below UI changes to be done in voyage information

 address --> drop location  name --> full name

 date --> remove pipe or keep a space

 vehicle --> introduce a format to vehicle ids Fix UI alignment issues.

**Mobile app**



**New story - CR** / Mobile Landing page / **[**

[and view the pending voyages](https://inivos.atlassian.net/browse/TN-613) [**DONE**](https://inivos.atlassian.net/browse/TN-613) **]**

Change the logo to the newly designed Transpomate logo. (contact marketing) Button names & UI should match Figma.

**Pending Voyage - CR / [**

[**DONE**](https://inivos.atlassian.net/browse/TN-619) **]**

add below items as Acceptance Criteria to

**)**

Need to add a loader if there is a delay when loading the voyage on the screen. In the pending voyages page, change the name to "pending voyage."

**Setup a UI review session and explore** (Responsible: BA )

Identify gaps between Figma and the App make changes to the plan to close them. (eg:- Passenger list - alignment issue for the call icon

- Developer)

**New story - CR / Voyage preview page / [**

**]**

In the preview page, we should show the *exact location.*

Remove voyage ID.

Need to add the re-arrangement in the voyage preview page as well.

should show the start and end locations in the route preview but there should not be drops (red pins) in those points.

[TN-614: [CR] As a Driver, I need to view a preview of the voyage before starting the voyage,](https://inivos.atlassian.net/browse/TN-614)

[TN-54: As a Mobile User, I want to view all the pending voyages, so that I can stay informed a](https://inivos.atlassian.net/browse/TN-54)

[So that I can view the route and be prepared](https://inivos.atlassian.net/browse/TN-614) [**DEV - TODO**](https://inivos.atlassian.net/browse/TN-614)

[bout the scheduled voyages for the day](https://inivos.atlassian.net/browse/TN-54) [**DONE**](https://inivos.atlassian.net/browse/TN-54)

[TN-619: [CR] As a Driver, I need to see the pending voyage, So that I can plan and prepare for the voyage](https://inivos.atlassian.net/browse/TN-619)

[TN-613: [CR] As a Driver I need to view the landing page of the mobile app, So that I can log in](https://inivos.atlassian.net/browse/TN-613)

|  |  |  |
| --- | --- | --- |
| **New story - CR / start voyage confirmation. / [** | [TN-615: [CR] As a Driver, I need to see a confirmation message when starting a voyag](https://inivos.atlassian.net/browse/TN-615) | |
| [e, So that I could either start the voyage or mark the missed passengers](https://inivos.atlassian.net/browse/TN-615) [**DONE**](https://inivos.atlassian.net/browse/TN-615) | | **]** |

In the confirmation (after starting voyage) change the

Back

to a Close .

Merge these 2 functions → Take picture and select picture.



**New story - CR / Odometer capture / [**

**]**

[TN-616: [CR] As a Driver, I need to take a picture of the odometer reading, So that I could send i](https://inivos.atlassian.net/browse/TN-616)

[t to the Transport Coordinator](https://inivos.atlassian.net/browse/TN-616) [**DEV - TODO**](https://inivos.atlassian.net/browse/TN-616)

 What should happen is when you take a picture, it should be shown as a preview instead of selecting.

(follow-up with PO if we should remove the existing feature - )

BA

|  |  |  |
| --- | --- | --- |
| **New story - CR / Odometer ending / [** | [TN-617: [CR] As a Driver, I need to enter the odometer reading, So that I could send it to the Tran](https://inivos.atlassian.net/browse/TN-617) | |
| [sport Coordinator for him to compare with the image](https://inivos.atlassian.net/browse/TN-617) [**TOGROOM**](https://inivos.atlassian.net/browse/TN-617) | | **]** |

 In the odometer ending page, remove the restriction of 5 decimals and need to add decimal values as well.



New story - CR / Change the status columns of the tables to an icon / [

[TN-618: [CR] As an Admin, I need to see clear icons on all th](https://inivos.atlassian.net/browse/TN-618)

**]**



[e view pages, So that I can quickly know the status](https://inivos.atlassian.net/browse/TN-618) [**DONE**](https://inivos.atlassian.net/browse/TN-618)

In the view pages, we need to show an icon/ toggle switch rather than having a label saying Enable or Disable , to show the status of the records so that it's easier for the users (admin / manager / TC) to see the status.

## Sample Sprint Retrospective - Sprint 15 (Day 10)

A sprint retrospective is a type of meeting within the Agile framework, when teams reflect on what went well and what could be improved for their next sprint. Retrospectives are essential to continuously improve your sprint process and ensure key learnings are incorporated for next time.

### Things that went well

EM

Spilled-over story points counts have been reduced.

BA

Completed most of the bugs.

QA3

None of the stories were put to on-hold state.

### Things that didn’t go well

Developer2

Some stories were delayed during code review state. Need a way to track R&D efforts during the sprint.